## Project Planner
Sprint 1 - Endurance |  |  |  |  | https://drive.google.com/drive/folders/1jUagPLvYAbyaNKjZqsO_FM9QZXwzorYe?usp=sharing
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | STAFF MEMBER(S) | PLAN START (Hours) | PLAN DURATION (Hours) | ACTUAL START (Hours) | ACTUAL DURATION (Hours) | PERCENT COMPLETE | HOURS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Develop a plan (Gantt chart) | Aidan, Jason, Bryan | 1 | 2 | 1 | 1 | 100% | bar: HOURS 1 to HOURS 2
Build requirements table | Aidan, Jason, Bryan | 3 | 2 | 2 | 2 | 100% | bar: HOURS 2 to HOURS 4
Requirements signoff table | Aidan, Jason, Bryan | 5 | 1 | 4 | 1 | 100% | bar: HOURS 4 to HOURS 6; HOURS 10
Create an Algorithm | Jason | 6 | 3 | 5 | 3 | 100% | bar: HOURS 5 to HOURS 8
Create a Flowchart | Bryan | 9 | 2 | 8 | 2 | 100% | bar: HOURS 8 to HOURS 10
Create Block Code | Jason | 11 | 6 | 10 | 2 | 100% | bar: HOURS 10 to HOURS 16
Sensor data diagram | Aidan | 17 | 4 | 12 | 1 | 100% | bar: HOURS 12; HOURS 17 to HOURS 20
Test Table | Aidan, Jason, Bryan | 21 | 1 | 13 | 2 | 100% | bar: HOURS 13 to HOURS 14; HOURS 21
Staffing Plan | Aidan, Jason, Bryan | 22 | 1 | 15 | 2 | 100% | bar: HOURS 15 to HOURS 16; HOURS 22
System Design Document | Aidan, Jason, Bryan | 23 | 5 | 17 | 4 | 100% | bar: HOURS 17 to HOURS 20; HOURS 23 to HOURS 27
Robot Video | Bryan | 28 | 1 | 21 | 1 | 100% | bar: HOURS 21; HOURS 28
Github Repository | Jason | 29 | 2 | 22 | 2 | 100% | bar: HOURS 22 to HOURS 23; HOURS 29 to HOURS 30
Robot Performance Test | Aidan, Jason, Bryan | 31 | 3 | 24 | 3 | 100% | bar: HOURS 24 to HOURS 26; HOURS 31 to HOURS 33